## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Amrit Veer Kaur(23758447)
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | the game board looks like …
|  | 3 | to set the dimensions of game board
|  | 4 | to have black color of background of gameboard
|  | 5 | different color for head and tail of snake
|  | 6 | to set prey on the board
|  | 7 | to move the snake
|  | 8 | to change the direction of snake when keys is pressed
|  | 9 | the snake to eat prey
|  | 10 | the snake to grow on eating prey
|  | 11 | to set the title"Snake Game" for the game

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Amrit Veer Kaur(23758447)
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form |  |  | 100%
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic |  |  | 20%
3.2.2 |  |  | prey logic |  |  | 20%
3.2.3 |  |  | gameboard logic |  |  | 20%
3.2.4 |  |  | snakegame logic
4 | Test and deploy the game |  |  | 3
4.1 |  | snakegame class |  |  | 10%
4.2 |  | gameboard class |  |  | 10%
4.3 |  | loginform class |  |  | 10%
5 | Document the game |  |  | 4 | 0%